| PAGE 1 · PURPOSE | GSQ GML DD&T · 1 / 5 |
| --- | --- |

One portal for how GSQ plants run DD&T

Leadership still prepares business reviews by stitching Jira, SPOT, site Power Apps, Power BI, and PowerPoint. The cost is not software — it is leadership time and inconsistent answers in the same meeting.

| Why | What | Who | Where |
| --- | --- | --- | --- |
| Purpose Run the review from a maintained system of record, not a slide factory. | The Glass One site-aware portal. Ten views. Reuse what exists; add what is missing. | Sponsors Joel Vincent · Executive sponsor Dean Santoro · Product lead | SPOT 1063647 Already live · Plan phase. Do not open a second project. |

| This is A single pane of glass for 18 GSQ Manufacturing & Labs sites. Site becomes a drop-down. Budget and Gantt sit on the same row. Site Heads type commentary and asks in the same portal. Thousand Oaks is the first business-review system of record. | This is not A new strategy, a second Jira, or a second SPOT. The portal does not overwrite dates or money. The $42k / 6-week figure is a thin shell only — it cannot prove Jira + SPOT + EDB together. |
| --- | --- |

Companion: Design Blueprint v1.3  ·  Business case MVP v2 Sept 2026  ·  TakOS Onboarding Readiness  ·  Confidential

| PAGE 2 · BUSINESS CASE | GSQ GML DD&T · 2 / 5 |
| --- | --- |

The value is hours back — proven first at Thousand Oaks

| 9,000 | 42 | $168k | 30,000 |
| --- | --- | --- | --- |
| hours / year Total value case · 18 sites ~500 hours per site per year | hours / site / month Deck assembly and status chasing the portal is meant to remove | Cost 10–12 weeks · ~2.5 FTE Recommended Marketplace order | hours total FY26 3,000 · FY27–29 9,000/yr On the SPOT 1063647 record |

Investment options — fund the product that can stop the decks

| Option | What you get | Time | Indicative cost |
| --- | --- | --- | --- |
| A. Thin shell | Site drop-down + wrap today’s tabs. No SPOT, no EDB, no Site Head input. | 6 weeks · 1 FTE | ~$42k |
| B. Recommended MVP | Live Jira + SPOT, combined Gantt, Capability, Site input, TO review freeze. | 10–12 weeks · ~2.5 FTE | ~$155–168k |
| C. Full case | Band B + EDB data-product bind + production network roadmap. | 12 weeks · ~3 FTE | ~$196k |

Business case §1 already quotes ~$168k / 6–12 weeks. Section 9 quotes ~$40k / 6 weeks. Those are different products. Recommend Band B at the $168k envelope. Do not approve Band A if the test is “executives stop building decks.” EDB binds as a gated increment inside the same order; the Capability Tracker embed is the fallback so the meeting still has an adoption view.

Value hypothesis on SPOT 1063647  ·  COP = Productivity Improvements  ·  Capture start 1 Dec 2026

| PAGE 3 · DESIGN SCHEMATIC | GSQ GML DD&T · 3 / 5 |
| --- | --- |

One Glass. Three systems of record. One write path.

Read-only: Jira · SPOT · EDB/Capability    Write: Dataverse commentary, asks, mapping, freeze pack

| PAGE 4 · WHAT LEADERS SEE | GSQ GML DD&T · 4 / 5 |
| --- | --- |

Same chrome on every tab. Site set once. The meeting runs here.

| One pager Big Rocks × FY | Gantt + Budget Dates vs spend | Budget Approve / actual | Capability Deploy + adopt | Business Review The meeting — new |
| --- | --- | --- | --- | --- |
| KPIs Honest counts | Risks Airtime only | Jira Live backlog | Site input Only write path — new | Network 34 programmes / 573 projects |

Target mockup — not a live app. Full view specs and live source screenshots are in the Design Blueprint.

| PAGE 5 · DECISION | GSQ GML DD&T · 5 / 5 |
| --- | --- |

Pilot at Thousand Oaks. Keep SPOT 1063647.

| 01 Fund Pilot | 02 Test Business Review Thousand Oaks | 03 Track Value in SPOT 1063647 | 04 Authorize onboarding of other sites |
| --- | --- | --- | --- |
| $155–168k · 10–12 weeks to the design blueprint. | First business-review system of record. UAT weeks 9–10. | File the funding request here. Align CAPEX to one number. | AIDPG Initiative → 1063647. Pattern-Fit · Intake gate. |

Go / no-go for Release 2

| One TO business review runs from the portal. | Site Head commentary is attributable. | Jira, SPOT, and Capability match in the room. | Leadership agrees the pattern scales. |
| --- | --- | --- | --- |

Next artefact is the AIDPG Initiative pointing at 1063647 — not a second SPOT. Week-1 work is a field workshop with PMO on Jira fields, SPOT access, and mapping quality. API access is the critical path; if it slips, the calendar slips.

Private and confidential. For internal use only.  ·  8 September 2026  ·  GSQ GML DD&T